## Slide 1: Management Activities in SE
Estimate of Effort and Costs.

## Slide 2: Types of Costs
Facilities: hardware, space, furniture, telephone, etc.
Software tools for designing software
Staff (effort): the biggest component of cost

## Slide 3: Pre-requisite to Estimating Effort
Understand the scope of the project to be built
Generate an estimate of size

## Slide 4: An Example
Software Module | Estimated LOC
User interface and control facilities (UICF) Two-dimensional geometric analysis (2DGA) Three-dimensional geometric analysis (3DGA) Database management (DBM) Computer graphics display facilities (CGDF) Peripheral control function (PCF) Design analysis modules (DAM) | 2,300 5,300 6,800 3,350 4,950 2,100 8,400
Estimated lines of code | 33,200
Effort?
Productivity?

## Slide 5: Estimating Size
The accuracy of a s/w project estimate is predicated on a number of things:
  The degree to which the planner has properly estimated the size of the product to be built
  The ability to translate the size estimate into human effort, calendar time, and dollars (required availability of past records)
  The degree to which the project plan reflects the abilities of the s/w team
  The stability of product requirements and the environment that supports the s/w engineering effort

## Slide 6: Estimating Size
Sizing represents the project planner’s first major challenge
Size refers to a quantifiable outcome of the s/w project (e.g. LOC and/or FP)

## Slide 7: Estimating Size
Three different sizing options are available
  Application points
  Function points
  Lines of source code

## Slide 8: Estimating Size and Effort
Example of baseline productivity metrics are LOC/pm or FP/pm

## Slide 9: An Example
Software Module | Estimated LOC
User interface and control facilities (UICF) Two-dimensional geometric analysis (2DGA) Three-dimensional geometric analysis (3DGA) Database management (DBM) Computer graphics display facilities (CGDF) Peripheral control function (PCF) Design analysis modules (DAM) | 2,300 5,300 6,800 3,350 4,950 2,100 8,400
Estimated lines of code | 33,200
Effort?
Productivity?

## Slide 10: An Example of LOC-Based Estimation
Estimated lines of code = W = 33,200
Let,
  Average productivity = X = 50 LOC/pd
  Labor rate = Y = $100 per day
So,
  Cost per line of code = Z = Y/X = $2
  Total estimated project cost = W*Z = $66,400
  Estimated effort = W/X = 664 person-days

## Slide 11: An Example of LOC-Based Estimation
Estimated lines of code = W = 33,200
Let,
  Average productivity = X = 600 LOC/pm
  Labor rate = Y = $5000 per month
So,
  Cost per line of code = Z = Y/X = ?
  Total estimated project cost = W*Z = ?
  Estimated effort = W/X = ?

## Slide 12: Estimation in Agile
Project Velocity
  The amount of work an agile team can complete in a sprint
Story Points
  The amount of effort required to implement a user story
User Story
  A requirement or general explanation of software feature

## Slide 13: Examples of User Stories
As a [customer], I want [shopping cart feature] so that [I can easily purchase items online].
As an [manager], I want to [generate a report] so that [I can understand which departments need more resources].
As a [customer], I want to [receive an SMS when the item is arrived] so that [I can go pick it up right away]

## Slide 14: Example

## Slide 15: Estimation in Agile
Project Velocity
  Story points completed ÷ Number of sprints